## Activity Risk Register
ACTIVITY-LEVEL RISKS | [23 empty] | Almost Certain | Medium | High | High | Extreme | Extreme | Almost Certain | 11 | 16 | 20 | 23 | 25
Assessing and Managing Activity Risk guideline
[24 empty] | Likely | Medium | Medium | High | High | Extreme | Likely | 7 | 12 | 17 | 21 | 24
Programme | [10 empty] | AMS number | [12 empty] | Possible | Low | Medium | Medium | High | Extreme | Possible | 4 | 8 | 13 | 18 | 22
[24 empty] | Unlikely | Low | Low | Medium | High | High | Unlikely | 2 | 5 | 9 | 14 | 19
Activity | [10 empty] | Active contracts | 0 | [7 empty] | Total activity issues | 0 |  |  | Rare | Low | Low | Medium | Medium | High | Rare | 1 | 3 | 6 | 10 | 15
[25 empty] | Negligible | Minor | Moderate | Major | Severe |  | Negligible | Minor | Moderate | Major | Severe
Summary |  | Overall, this Activity's risk is … (overwrite with any necessary comment) | [8 empty] | Overall risk |  |  | 0 | [5 empty] | Total activity open risks | 2
Risk Identification | [7 empty] | Risk Assessment Rate the activity risk with existing combined controls in place. One score per risk. | [7 empty] | Risk and Issue Management
Risk no. | Date Raised | Risk Category | Risk Description | Source of Risk |  |  | Potential Impacts | Current Controls |  | Likelihood | Consequence | Overall risk rating | Risk Score | R# | Action Required | Risk Owner | Treatment Description | Treatment Manager | Date Last Reviewed | Next Review Date | Status of risk | Comments/History
Activity Managers: In the case of existing activities, you can migrate the data from your activity risk register into this template or provide a hyperlink to the existing risk register here (Delete this text)
|  | Health & Safety | See Health & Safety risks below | [10 empty] | 0 | See below |  | See below |  |  |  | Open |  | Africa
|  | Activity Design Risks | Insert link to ADD here | [17 empty] | Open |  | ASEAN | [12 empty] | Construction | High
1 | [22 empty] | Climate Change | [12 empty] | Working at heights | High
2 | [22 empty] | Cook Islands | [12 empty] | Medical work | High
3 | [22 empty] | Economic Development | [12 empty] | Operating Major Plant & Machinery | High
4 | [22 empty] | Fiji | [12 empty] | Work on Farms | High
5 | [22 empty] | Human Development | [12 empty] | Electricity / Gas | High
6 | [22 empty] | Humanitarian and Disaster Management | [12 empty] | Chemicals & hazardous materials | High
7 | [22 empty] | Indonesia | [12 empty] | UXO | High
8 | [22 empty] | Kiribati | [12 empty] | Aviation | High
9 | [22 empty] | Latin America & Caribbean | [12 empty] | Underwater | High
10 | [22 empty] | Multilateral Agencies | [12 empty] | Policing | High
[23 empty] | Myanmar | [12 empty] | USAR | High
[23 empty] | Nauru | [12 empty] | Prisons | High
CONTRACT-LEVEL (HEALTH & SAFETY) RISKS | [22 empty] | Niue | [12 empty] | Other - High risk | High
Aid Programme Health and Safety Procedures | [22 empty] | Other Asia | [12 empty] | Other – Medium Risk | Medium
Contractor 1 | [10 empty] | Koru number | [8 empty] | Incidents | 0 |  | Pacific Economic | [12 empty] | Office work | Low
[23 empty] | Pacific Energy & Infrastructure | [12 empty] | Activity Design | Low
|  |  | Inherent risk |  |  | 0 |  |  |  |  | Overall risk |  |  | 0 | [5 empty] | Open risks | 0 |  | Pacific HEF | [12 empty] | Other - Low risk | Low
Pacific Regional Agencies
Hazard Identification | [6 empty] | Hazard Controls |  |  | Risk Assessment Rate the H&S risk with existing combined controls in place. One score per hazard. | [6 empty] | Risk Management | [5 empty] | Pacific Transformational
Hazard / risk no. | Location | Hazard Category | Hazard Name |  | Inherent risk (rate the risk before controls are applied) |  | List of Hazard Controls to manage risk of harm |  | Is the control currently in place? | Likelihood | Consequence | Overall risk rating (see Matrix tab) |  | R# | Date risk assessed | Names of manager and staff rep completing risk assessment for each hazard required | Action plan to eliminate or mitigate the risk is in place | Person responsible | Date last reviewed | Next review date | Status of risk |  | Papua New Guinea
HAZARD TYPE: General in-country / regional hazards where workers undertake work List the countries / regions where workers will undertake work and allocate inherent risk rating as per current risk rating on SafeTravel. Where a country / region has a different risk rating, add a new row to capture the different risk rating. | [22 empty] | Partnerships & Funds
1 |  | Various hazards associated with working in the relevant location or country |  |  |  |  | Partner / Contractor to apply its hazard controls in accordance with H&S Acknowledgement Form |  |  | See Partner / Contractor's H&S Acknowledgement Form [insert link] |  |  |  |  | N/A | [7 empty] | Samoa
2 |  | Various hazards associated with working in the relevant location or country |  |  |  |  | Partner / Contractor to apply its hazard controls in accordance with H&S Acknowledgement Form |  |  | See Partner / Contractor's H&S Acknowledgement Form linked above |  |  |  |  | N/A | [7 empty] | Scholarships
Solomon Islands
Strategic Evaluation and Research
HAZARD TYPE: Worktype - Hazards inherent in the nature of the work being undertaken Select the worktypes from the dropdown menu that best reflects the hazards that workers will be exposed to | [22 empty] | Timor-Leste
| N/A | [5 empty] | Partner / Contractor to apply its hazard controls in accordance with its Safety Plan |  |  | See Partner / Contractor's Safety Plan [insert link] |  |  |  |  | N/A | [7 empty] | Tokelau
HAZARD TYPE: Special hazards - any other hazards not captured above Consider all other hazards to the health and safety of workers under this contract and complete a new row for each hazard. Add any emerging risks as they arise. | [22 empty] | Tokelau
Tuvalu
Vanuatu
CONTRACT-LEVEL (HEALTH & SAFETY) RISKS
Contractor 2 | [10 empty] | Koru number | [8 empty] | Incidents | 0
|  |  | Inherent risk |  |  | 0 |  |  |  |  | Overall risk |  |  | 0 | [5 empty] | Open risks | 0
Hazard Identification | [6 empty] | Hazard Controls |  |  | Risk Assessment Rate the H&S risk with existing combined controls in place. One score per hazard. | [6 empty] | Risk Management
Hazard / risk no. | Location | Hazard Category | Hazard Name |  | Inherent risk (rate the risk before controls are applied) |  | List of Hazard Controls to manage risk of harm |  | Is the control currently in place? | Likelihood | Consequence | Overall risk rating (see Matrix tab) |  | R# | Date risk assessed | Names of manager and staff rep completing risk assessment for each hazard required | Action plan to eliminate or mitigate the risk is in place | Person responsible | Date last reviewed | Next review date | Status of risk
HAZARD TYPE: General in-country / regional hazards where workers undertake work List the countries / regions where workers will undertake work and allocate inherent risk rating as per current risk rating on SafeTravel. Where a country / region has a different risk rating, add a new row to capture the different risk rating.
1 |  | Various hazards associated with working in the relevant location or country |  |  |  |  | Partner / Contractor to apply its hazard controls in accordance with H&S Acknowledgement Form |  |  | See Partner / Contractor's H&S Acknowledgement Form [insert link] |  |  |  |  | N/A
2 |  | Various hazards associated with working in the relevant location or country |  |  |  |  | Partner / Contractor to apply its hazard controls in accordance with H&S Acknowledgement Form |  |  | See Partner / Contractor's H&S Acknowledgement Form linked above |  |  |  |  | N/A
HAZARD TYPE: Worktype - Hazards inherent in the nature of the work being undertaken Select the worktypes from the dropdown menu that best reflects the hazards that workers will be exposed to
| N/A | [5 empty] | Partner / Contractor to apply its hazard controls in accordance with its Safety Plan |  |  | See Partner / Contractor's Safety Plan [insert link] |  |  |  |  | N/A
HAZARD TYPE: Special hazards - any other hazards not captured above Consider all other hazards to the health and safety of workers under this contract and complete a new row for each hazard. Add any emerging risks as they arise.
CONTRACT-LEVEL (HEALTH & SAFETY) RISKS
Contractor 3 | [10 empty] | Koru number | [8 empty] | Incidents | 0
|  |  | Inherent risk |  |  | 0 |  |  |  |  | Overall risk |  |  | 0 | [5 empty] | Open risks | 0
Hazard Identification | [6 empty] | Hazard Controls |  |  | Risk Assessment Rate the H&S risk with existing combined controls in place. One score per hazard. | [6 empty] | Risk Management
Hazard / risk no. | Location | Hazard Category | Hazard Name |  | Inherent risk (rate the risk before controls are applied) |  | List of Hazard Controls to manage risk of harm |  | Is the control currently in place? | Likelihood | Consequence | Overall risk rating (see Matrix tab) |  | R# | Date risk assessed | Names of manager and staff rep completing risk assessment for each hazard required | Action plan to eliminate or mitigate the risk is in place | Person responsible | Date last reviewed | Next review date | Status of risk
HAZARD TYPE: General in-country / regional hazards where workers undertake work List the countries / regions where workers will undertake work and allocate inherent risk rating as per current risk rating on SafeTravel. Where a country / region has a different risk rating, add a new row to capture the different risk rating.
1 |  | Various hazards associated with working in the relevant location or country |  |  |  |  | Partner / Contractor to apply its hazard controls in accordance with H&S Acknowledgement Form |  |  | See Partner / Contractor's H&S Acknowledgement Form [insert link] |  |  |  |  | N/A
2 |  | Various hazards associated with working in the relevant location or country |  |  |  |  | Partner / Contractor to apply its hazard controls in accordance with H&S Acknowledgement Form |  |  | See Partner / Contractor's H&S Acknowledgement Form linked above |  |  |  |  | N/A
HAZARD TYPE: Worktype - Hazards inherent in the nature of the work being undertaken Select the worktypes from the dropdown menu that best reflects the hazards that workers will be exposed to
| N/A | [5 empty] | Partner / Contractor to apply its hazard controls in accordance with its Safety Plan |  |  | See Partner / Contractor's Safety Plan [insert link] |  |  |  |  | N/A
HAZARD TYPE: Special hazards - any other hazards not captured above Consider all other hazards to the health and safety of workers under this contract and complete a new row for each hazard. Add any emerging risks as they arise.
CONTRACT-LEVEL (HEALTH & SAFETY) RISKS
Contractor 4 | [10 empty] | Koru number | [8 empty] | Incidents | 0
|  |  | Inherent risk |  |  | 0 |  |  |  |  | Overall risk |  |  | 0 | [5 empty] | Open risks | 0
Hazard Identification | [6 empty] | Hazard Controls |  |  | Risk Assessment Rate the H&S risk with existing combined controls in place. One score per hazard. | [6 empty] | Risk Management
Hazard / risk no. | Location | Hazard Category | Hazard Name |  | Inherent risk (rate the risk before controls are applied) |  | List of Hazard Controls to manage risk of harm |  | Is the control currently in place? | Likelihood | Consequence | Overall risk rating (see Matrix tab) |  | R# | Date risk assessed | Names of manager and staff rep completing risk assessment for each hazard required | Action plan to eliminate or mitigate the risk is in place | Person responsible | Date last reviewed | Next review date | Status of risk
HAZARD TYPE: General in-country / regional hazards where workers undertake work List the countries / regions where workers will undertake work and allocate inherent risk rating as per current risk rating on SafeTravel. Where a country / region has a different risk rating, add a new row to capture the different risk rating.
1 |  | Various hazards associated with working in the relevant location or country |  |  |  |  | Partner / Contractor to apply its hazard controls in accordance with H&S Acknowledgement Form |  |  | See Partner / Contractor's H&S Acknowledgement Form [insert link] |  |  |  |  | N/A
2 |  | Various hazards associated with working in the relevant location or country |  |  |  |  | Partner / Contractor to apply its hazard controls in accordance with H&S Acknowledgement Form |  |  | See Partner / Contractor's H&S Acknowledgement Form linked above |  |  |  |  | N/A
HAZARD TYPE: Worktype - Hazards inherent in the nature of the work being undertaken Select the worktypes from the dropdown menu that best reflects the hazards that workers will be exposed to
| N/A | [5 empty] | Partner / Contractor to apply its hazard controls in accordance with its Safety Plan |  |  | See Partner / Contractor's Safety Plan [insert link] |  |  |  |  | N/A
HAZARD TYPE: Special hazards - any other hazards not captured above Consider all other hazards to the health and safety of workers under this contract and complete a new row for each hazard. Add any emerging risks as they arise.
CONTRACT-LEVEL (HEALTH & SAFETY) RISKS
Contractor 5 | [10 empty] | Koru number | [8 empty] | Incidents | 0
|  |  | Inherent risk |  |  | 0 |  |  |  |  | Overall risk |  |  | 0 | [5 empty] | Open risks | 0
Hazard Identification | [6 empty] | Hazard Controls |  |  | Risk Assessment Rate the H&S risk with existing combined controls in place. One score per hazard. | [6 empty] | Risk Management
Hazard / risk no. | Location | Hazard Category | Hazard Name |  | Inherent risk (rate the risk before controls are applied) |  | List of Hazard Controls to manage risk of harm |  | Is the control currently in place? | Likelihood | Consequence | Overall risk rating (see Matrix tab) |  | R# | Date risk assessed | Names of manager and staff rep completing risk assessment for each hazard required. | Action plan to eliminate or mitigate the risk is in place | Person responsible | Date last reviewed | Next review date | Status of risk
HAZARD TYPE: General in-country / regional hazards where workers undertake work List the countries / regions where workers will undertake work and allocate inherent risk rating as per current risk rating on SafeTravel. Where a country / region has a different risk rating, add a new row to capture the different risk rating.
1 |  | Various hazards associated with working in the relevant location or country |  |  |  |  | Partner / Contractor to apply its hazard controls in accordance with H&S Acknowledgement Form |  |  | See Partner / Contractor's H&S Acknowledgement Form [insert link] |  |  |  |  | N/A
2 |  | Various hazards associated with working in the relevant location or country |  |  |  |  | Partner / Contractor to apply its hazard controls in accordance with H&S Acknowledgement Form |  |  | See Partner / Contractor's H&S Acknowledgement Form linked above |  |  |  |  | N/A
HAZARD TYPE: Worktype - Hazards inherent in the nature of the work being undertaken Select the worktypes from the dropdown menu that best reflects the hazards that workers will be exposed to
| N/A | [5 empty] | Partner / Contractor to apply its hazard controls in accordance with its Safety Plan |  |  | See Partner / Contractor's Safety Plan [insert link] |  |  |  |  | N/A
HAZARD TYPE: Special hazards - any other hazards not captured above Consider all other hazards to the health and safety of workers under this contract and complete a new row for each hazard. Add any emerging risks as they arise.
Note on T34: MFAT Activity Manager to follow up on the required action
Note on B36: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country/location.
Note on F36: Inherent Risk is determined by SafeTravel rating for that location or country. See: https://www.safetravel.govt.nz/travel-advisories-destination
Note on J36: The control is the completion of the H&S Acknowledgement Form
Note on K36: Attach link to signed Form
Note on P36: All grey cells in the Health and Safety component of the Register do NOT need to be populated
Note on R36: Select from dropdown menu
Note on B37: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country/location.
Note on B38: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country.
Note on B39: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country.
Note on C41: Select most appropriate description from dropdown menu.
Note on D41: Outline the work to be undertaken
Note on F41: Inherent risk automatically populates. Adjust manually if necessary by using the Risk Matrix to determine inherent risk of the work (before any controls in place)
Note on J41: Control is the Safety Plan
Note on M41: Use Risk Matrix to determine the residual risk of the work (once all controls are in place)
Note on R41: Select from dropdown menu
Note on D43: Describe the hazard, potential issue or provide outline of incidents occured
Note on T57: MFAT Activity Manager to follow up on the required action
Note on B59: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country/location.
Note on F59: Inherent Risk is determined by SafeTravel rating for that location or country. See: https://www.safetravel.govt.nz/travel-advisories-destination
Note on J59: The control is the completion of the H&S Acknowledgement Form
Note on K59: All grey cells in the Health and Safety component of the Register do NOT need to be populated
Note on R59: Select from dropdown menu
Note on B60: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country/location.
Note on B61: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country.
Note on B62: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country.
Note on C64: Select most appropriate description from dropdown menu.
Note on D64: Outline the work to be undertaken
Note on F64: Inherent risk automatically populates. Adjust manually if necessary by using the Risk Matrix to determine inherent risk of the work (before any controls in place)
Note on J64: Control is the Safety Plan
Note on M64: Use Risk Matrix to determine the residual risk of the work (once all controls are in place)
Note on R64: Select from dropdown menu
Note on D66: Describe the hazard, potential issue or provide outline of incidents occured
Note on T80: MFAT Activity Manager to follow up on the required action
Note on B82: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country/location.
Note on F82: Inherent Risk is determined by SafeTravel rating for that location or country. See: https://www.safetravel.govt.nz/travel-advisories-destination
Note on J82: The control is the completion of the H&S Acknowledgement Form
Note on K82: All grey cells in the Health and Safety component of the Register do NOT need to be populated
Note on R82: Select from dropdown menu
Note on B83: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country/location.
Note on B84: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country.
Note on B85: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country.
Note on C87: Select most appropriate description from dropdown menu.
Note on D87: Outline the work to be undertaken
Note on F87: Inherent risk automatically populates. Adjust manually if necessary by using the Risk Matrix to determine inherent risk of the work (before any controls in place)
Note on J87: Control is the Safety Plan
Note on M87: Use Risk Matrix to determine the residual risk of the work (once all controls are in place)
Note on R87: Select from dropdown menu
Note on D89: Describe the hazard, potential issue or provide outline of incidents occured
Note on T103: MFAT Activity Manager to follow up on the required action
Note on B105: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country/location.
Note on F105: Inherent Risk is determined by SafeTravel rating for that location or country. See: https://www.safetravel.govt.nz/travel-advisories-destination
Note on J105: The control is the completion of the H&S Acknowledgement Form
Note on K105: All grey cells in the Health and Safety component of the Register do NOT need to be populated
Note on R105: Select from dropdown menu
Note on B106: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country/location.
Note on B107: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country.
Note on B108: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country.
Note on C110: Select most appropriate description from dropdown menu.
Note on D110: Outline the work to be undertaken
Note on F110: Inherent risk automatically populates. Adjust manually if necessary by using the Risk Matrix to determine inherent risk of the work (before any controls in place)
Note on J110: Control is the Safety Plan
Note on M110: Use Risk Matrix to determine the residual risk of the work (once all controls are in place)
Note on R110: Select from dropdown menu
Note on D112: Describe the hazard, potential issue or provide outline of incidents occured
Note on T126: MFAT Activity Manager to follow up on the required action
Note on B128: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country/location.
Note on F128: Inherent Risk is determined by SafeTravel rating for that location or country. See: https://www.safetravel.govt.nz/travel-advisories-destination
Note on J128: The control is the completion of the H&S Acknowledgement Form
Note on K128: All grey cells in the Health and Safety component of the Register do NOT need to be populated
Note on R128: Select from dropdown menu
Note on B129: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country/location.
Note on B130: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country.
Note on B131: Enter the name of the country or location in which workers are required to work. If more than one country or locations within one country have different risk ratings, create a new 'Hazard Type A' row for each country.
Note on C133: Select most appropriate description from dropdown menu.
Note on D133: Outline the work to be undertaken
Note on F133: Inherent risk automatically populates. Adjust manually if necessary by using the Risk Matrix to determine inherent risk of the work (before any controls in place)
Note on J133: Control is the Safety Plan
Note on M133: Use Risk Matrix to determine the residual risk of the work (once all controls are in place)
Note on R133: Select from dropdown menu
Note on D135: Describe the hazard, potential issue or provide outline of incidents occured

## Likelihood, Consequence Matrix
Likelihood and Consequence Matrix
| LIKELIHOOD | Almost Certain • Expected to occur in most circumstances • Occurs every 6 months or more frequently • >90% chance of event occurring | Medium 11 | High 16 | High 20 | Extreme 23 | Extreme 25
|  | Likely • Will probably occur in most circumstances • Occurs every 6-12 months • 75%-90% chance of event occurring | Medium 7 | Medium 12 | High 17 | High 21 | Extreme 24
|  | Possible • Could occur at some stage • Occurs every 12-24 months • 50%-75% chance of event occurring | Low 4 | Medium 8 | Medium 13 | High 18 | Extreme 22
|  | Unlikely • Will occur in exceptional circumstances • Occurs every 24-48 months • 10%-50% chance of event occurring | Low 2 | Low 5 | Medium 9 | High 14 | High 19
|  | Rare • May occur in exceptional circumstances • Occurs every 4 or more years • <10% chance of event occurring | Low 1 | Low 3 | Medium 6 | Medium 10 | High 15
| CONSEQUENCE |  | Negligible | Minor | Moderate | Major | Severe
Operational | Health & Safety |  | • Insignificant injury, no lost time, no long term effects | • First aid injury, minimal lost time, no long term effects | • Off-site medical attention required, some lost time • Reversible disability or injuries | • Considerable hospitalisation required, significant time lost • Irreversible disability to one person | • One or more fatalities • Unable to return to work • Significant irreversible disability to more than one person
| Legal |  | • Few legal issues, non-compliances or breaches of legislation | • Minor legal issues, non-compliances and breaches of legislation | • Breach of legislation with investigation • Requires reporting to authority | • Major breach of legislation • Some legal action possible (nationally or internationally) • Requires detailed reporting to authority with ongoing monitoring, prosecution and or/fines possible | • Serious breach of legislation • Significant prosecution and fines expected • Significant legal action expected (nationally or internationally)
Financial | Financial |  | • Impact on activity up to 10% of activity budget or impact of <$50,000 (whichever is higher) • <$1,000 fraud incident | • Impact on activity 11%-20% of activity budget or impact of $50,000-$99,999 (whichever is higher) • $1,000-$19,999 fraud incident | • Impact on activity 21%-30% of activity budget or impact of $100,000-$499,999 (whichever is higher) • $20,000-$99,999 fraud incident | • Impact on activity 31%-40% of activity budget or impact of $500,000-$999,999 (whichever is higher) • $100,000-$249,999 fraud incident | • Impact on activity over 40% of activity budget or impact of $1,000,000+ (whichever is higher) •$250,000+ fraud incident
Development | Programme Delivery & Results |  | • <10% time delay to project delivery • Routine operational niggles/deficiencies of no material impact • No quality concerns • Delivers results for over 70% of intended beneficiaries | • 10%-20% time delay to project delivery • Some quality concerns • Few planned outcomes not achieved • Delivers results for 51-70% of intended beneficiaries | • 20%-30% time delay to project delivery • Some quality compromises • Some planned outcomes may not be achieved • Delivers results for 36-50% of intended beneficiaries | • >30% time delay to project delivery • Delay extends beyond End of Financial Year • Significant quality concerns or compromises • Few planned outcomes expected to be met • Delivers results for 21-35% of intended beneficiaries | • Indefinite delay • Delay extends beyond End of Financial Year • Quality failure • No planned outcomes expected to be met • Delivers results for <20% intended beneficiaries
| Environment & Social |  | • No adverse impacts | • Minimal adverse impacts with no long-term effects | • Potential to cause site specific adverse impacts which may be prevented or mitigated • Some people in target area unable to benefit | • Potential to cause significant adverse impacts (irreversible or unprecedented) which extend beyond physical footprint of the Activity • Some people in target area disadvantaged | • Significant adverse impacts (irreversible or unprecedented) which extend beyond physical footprint of the Activity • Some people in target area significantly disadvantaged
Reputation | Stakeholders |  | • Little stakeholder interest | • Relationship difficulties with stakeholders | • On-going relationship issues with stakeholders • Temporary damage to bilateral relationship • Minister expresses dissatisfaction to CE/SLT • Partner Government expresses dissatisfaction to Ministry or Post leadership | • Publically visible breakdown in relationships with stakeholders • Significant damage to bilateral relationship • Minister or Partner Government is politically embarrassed and publically expresses dissatisfaction with Ministry | • Serious and continuing stakeholder criticism expressed publically • Long-term major damage to bilateral relationship • Minister or Partner Government publicly expresses loss of confidence in the Chief Executive or Ministry
| Reputation |  | • No visible impact on the Ministry reputation • Minimal local media attention • Consequences can be dealt with by routine operations | • Some national media attention • Minimal impacts to NZ international reputation | • Some impact to NZ international reputation • A section of NZ public dissatisfied with Ministry • Adverse national media attention • Adverse in-country media attention • Independent investigation commissioned internally | • Major impacts to NZ international reputation • Serious adverse national media attention • Adverse regional media attention • Some sections of NZ public dissatisfied with Ministry • Public inquiry into Ministry activity | • Serious adverse impacts to NZ international reputation • Significant and continuing adverse national media attention • Broad international media attention • Significant loss of confidence in Ministry from multiple sections of NZ public

## Escalation & Action
Risk Acceptance, Escalation and Action table for Activity Risks
See Health and Safety Procedures for escalation and action table for H&S risks
Controlled Level of Risk | Required Actions | Escalate to (via line management):
Extreme | Risk must be treated. Immediate attention is required. Develop, document and agree appropriate treatment strategies (including implementation timeframes). Implement regular review and monitoring processes, including reporting that details the progress of treatment plans. Consult with AUR regarding treatment strategies, review processes etc. Risk to be included in SLT and Governance Board reporting. | Escalate and discuss key risk details with DS-PDG: • DS-PDG to escalate and discuss with Chief Executive/SLT if required • Chief Executive to escalate and discuss with the Minister, if required.
High | Risk must be treated. Attention is required as soon as possible. Develop, document and agree appropriate treatment strategies (including implementation timeframes). Implement regular review and monitoring processes, including reporting that details the progress of treatment plans. Risk to be included in Group and Steering Committee reporting. | Escalate and discuss key risk details with appropriate divisional manager. Director to escalate and discuss with DS-PDG, if required.
Medium | Risk should be monitored. (Note : Managers should consider treating a Medium/Yellow risk if they are concerned with: • the level of uncertainty that exists with the risk e.g. lots of unknowns • the risk is volatile e.g. the risk has the potential to rapidly escalate into a risk event.) Attention is required in a timely manner. Implement appropriate review and monitoring processes. | Escalate and discuss key risk details with appropriate Unit Manager/Development Counsellor/HOM if necessary.
Low | Risk can be accepted. Review periodically to ensure the level of risk is not increasing and further action is not required. | N/A

## Risk Register Exemplar
ACTIVITY-LEVEL RISKS
Programme |  | Fiji | [8 empty] | AMS number | x459697
Activity |  | Drought Response | [8 empty] | Active contracts | 1 | [6 empty] | Total activity issues | 0
Summary |  | Overall, this Activity's risk is High | [8 empty] | Overall risk | High | 3 | [5 empty] | Total activity open risks | 3
Risk Identification | [7 empty] | Risk Assessment Rate the activity risk with existing combined controls in place. One score per risk. | [6 empty] | Risk and Issue Management
Risk no. | Date Raised | Risk Category | Risk Description | Source of Risk |  |  | Potential Impacts | Current Controls |  | Likelihood | Consequence | Overall risk rating | R# | Action Required | Risk Owner | Treatment Description | Treatment Manager | Date Last Reviewed | Next Review Date | Status of risk | Comments/History
This register is an exemplar, see template on other tab
| 2016-05-17 | Health & Safety | See Health & Safety risks below | [8 empty] | Medium | 2 | See below | Bugs Bunny | See below |  | 2016-05-17 | 2016-08-17 | Open |  | Almost Certain | Medium | High | High | Extreme | Extreme | Afghanistan | Almost Certain | Medium | High | High | Extreme | Extreme
|  | Activity Design Risks | http://o-wln-gdm/Functions/InternationalDevelopment/Programmes-Country/ADDexemplarlink | [8 empty] | Medium |  |  | Bugs Bunny | Project steering committee reviews ADD risk management on a six monthly basis This six monthly meeting reviews the progress against the supplier's treatment action plan | Bugs Bunny | 2016-05-17 | 2016-11-17 | Open
1 | 2016-05-17 | Reputation | If the water tanks are not delivered in time for the drought season the Government will lose faith in NZ's ability to deliver through the Aid Programme. | Delays in equipment manufacture or transportation |  |  | Equipment is not delivered prior to the drought season | Contract with supplier, stipulated deliver date will be in advance of the drought season. |  | Possible | Major | High | 3 | Treat Risk | Bugs Bunny | Insert regular reporting milestones in contract with supplier. Diary regular updates for Govt regarding progress and potential delays. Ensure that the Govt has a contingency plan in place to access water tanks during the drought season. | Daffy Duck | 2016-05-17 | 2016-08-17 | Open |  | Likely | Medium | Medium | High | High | Extreme | Africa Regional | Likely | Medium | Medium | High | High | Extreme
2 | [21 empty] | Possible | Low | Medium | Medium | High | Extreme | ASEAN Regional | Possible | Low | Medium | Medium | High | Extreme
3 | [21 empty] | Unlikely | Low | Low | Medium | High | High | Cook Islands | Unlikely | Low | Low | Medium | High | High
4 | [21 empty] | Rare | Low | Low | Medium | Medium | High | Economic Development | Rare | Low | Low | Medium | Medium | High
5 | [22 empty] | Negligible | Minor | Moderate | Major | Severe | Fiji |  | Negligible | Minor | Moderate | Major | Severe
6 | [27 empty] | French Polynesia
7 | [27 empty] | Human Development
8 | [21 empty] | Almost Certain | 11 | 16 | 20 | 23 | 25 | Humanitarian and Disaster Management | Almost Certain | 11 | 16 | 20 | 23 | 25
9 | [21 empty] | Likely | 7 | 12 | 17 | 21 | 24 | Indonesia | Likely | 7 | 12 | 17 | 21 | 24
10 | [21 empty] | Possible | 4 | 8 | 13 | 18 | 22 | Kiribati | Possible | 4 | 8 | 13 | 18 | 22
[22 empty] | Unlikely | 2 | 5 | 9 | 14 | 19
CONTRACT-LEVEL (HEALTH & SAFETY) RISKS | [21 empty] | Rare | 1 | 3 | 6 | 10 | 15
[23 empty] | Negligible | Minor | Moderate | Major | Severe
Contractor 1 |  | Lightening Limited | [8 empty] | Koru number | 40677 | [6 empty] | Incidents | 1
|  |  | Inherent risk |  | High | 3 |  |  |  |  | Overall risk | Medium | 2 | [5 empty] | Open risks | 2
Hazard Identification | [6 empty] | Hazard Controls |  |  | Risk Assessment Rate the H&S risk with existing combined controls in place. One score per hazard. | [5 empty] | Risk Management
Hazard / risk no. | Location | Hazard Category | Hazard Name |  | Inherent risk (rate the risk before controls are applied) |  | List of Hazard Controls to manage risk of harm |  | Is the control currently in place? | Likelihood | Consequence | Overall risk rating (see Matrix tab) | R# | Date risk assessed | Names of manager and staff rep completing risk assessment for each hazard required. | Action plan to eliminate or mitigate the risk is in place | Name of person responsible for ensuring action or plan is completed | Date the action or plan will be completed | Review date | Status of risk
HAZARD TYPE A: General in-country / regional hazards Add a new row for each country which this contract requires workers to undertake work.
1 | Fiji | Various hazards associated with working in the relevant country or countries |  |  | Low | 1 | Contract Manager communicates relevant hazards to Contractor using the H&S Acknowledgement Form regarding SafeTravel and related websites. Contractor to familiarise and confirm same to MFAT |  | Yes | N/A |  | Low | 1 | N/A |  | Form received from Contractor | Mick Jagger | 2016-05-18 | 2016-05-18 | Closed
HAZARD TYPE B: Hazards inherent in the nature of the work being undertaken
| N/A | Various hazards associated with the nature of the work being undertaken (e.g. construction, hospitals) |  |  | High | 3 | Contractor to apply its hazard controls in accordance with its project safety management plan (or equivalent) |  | Yes | See Contractor's safety documentation |  | Medium | 2 | N/A |  | Contractor has provided safety documentation which is being reviewed. | Mick Jagger | 2016-05-18 | 2016-05-18 | Closed
[7 empty] | MFAT receives reports via general reporting and incident reporting. MFAT monitors activity and Contractor's safety performance |  | Yes | [7 empty] | Mick Jagger | 2016-05-18 | 2016-06-30 | Open
HAZARD TYPE C: Special hazards - any other hazards not captured above Consider all other hazards to the health and safety of workers under this contract and complete a new row for each hazard.
1 | Fiji | Restoration of electrical lines network | Transport /Driving Difficulties due to lack of specific vehicles |  | High | 3 | MFAT to consult with contractor and they have advised they: Take extra care when drving Are cautious when using non standard vehicles Limit the use of non standard vehicles if possible If using cherry picker ensure ground is firm and flat Familiarise their workers with non standard vehicle prior to use Go slowly due to condition of road surfaces post cyclone MFAT Contract Manager to monitor |  | Yes | Possible | Moderate | Medium | 2 | 2016-05-18 | Mick Jagger | Activity Manager to confirm list of Actions by email to Contractor and confirm acknowledgement receipt received and actions taken Contractor to advise immediately of any Accidents/incidents and Near Misses Activity Manager to take further actions if required | Mick Jagger | 2016-05-18 | 2016-05-18 | Open
2 |  |  | Equipment (Non standard linesman equipment being used) |  | High | 3 | MFAT to consult with contractors and they have advised that they: Limit the use of non-standard equipment where possible Ensure any alternative equipment is assesssed initially as being suitable Familiarise their workers with equipment prior to use If unsure, they do not use Ensure if training is required that it is given MFAT Contract Manager to monitor |  | Yes | Possible | Moderate | Medium | 2 | 2016-05-18 | Mick Jagger | Activity Manager to confirm list of Actions by email to Contractor and confirm acknowledgement receipt received and actions taken Contractor to advise immediately of any Accidents/incidents and Near Misses Activity Manager to take further actions if required | Mick Jagger | 2016-05-18 | 2016-05-18 | Open
|  | Health | Confirmed case of Zika virus |  | High | 3 | MFAT to consult with contractor and refer to the Health section on Safetravel website and refer to steps to be taken to avoid contracting mosquito borne viruses and for advice / precautions following infection MFAT Activity Manager recorded on HR Kiost and will monitor |  | Yes | Possible | Moderate | Medium | 2 | 2016-05-18 | Mick Jagger | Activity Manager to confirm list of Actions by email to Contractor and confirm acknowledgement receipt received and actions taken Contractor to advise immediately of any Accidents/incidents and Near Misses Activity Manager to take further actions if required | Mick Jagger | 2016-05-18 | 2016-05-18 | Incident